## planning
Project name |  | Quarter | Q3 2015 |  |  |  |  | Q4 2015 | [12 empty] | Q1 2016 | [12 empty] | Q2 2016 | [12 empty] | Q3 2016 | [12 empty] | Q4 2016 | [12 empty] | Q1 2017 | [12 empty] | Q2 2017
timing overview |  | month | Sep |  |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  |  | Jul |  |  |  | Aug |  |  |  | Sep |  |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun
2015-09-08 | who | Monday | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26
activity |  | week nr | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
[19 empty] | n. yr. | [5 empty] | chinese n.y. | [24 empty] | summer | [21 empty] | n. yr. |  |  |  | chinese n.y.
Project plan | bar: Sep 31 36 to Nov 9 46
Prepare project plan | ab | bar: Sep 31 36 to Sep 28 40
Feedback from stakeholders and iteration | ab | bar: Oct 5 41 to Oct 19 43
Budget approval | cd | bar: Oct 19 43 to Nov 2 45
Project approval | ef | bar: Nov 9 46
project approved
Kickoff | bar: Nov 16 47 to Dec 21 52
prepare kickoff | ab | bar: Nov 16 47 to Dec 30 49
kickoff workshop | cd | bar: Dec 7 50
report | cd | bar: Dec 14 51 to Dec 21 52
kickoff reported
Concept stage | bar: Dec 28 53 to Feb 15 7
Brief agencies | ef | bar: Dec 28 53 to Jan 4 1
Concept design | gh | bar: Jan 11 2 to Jan 25 4
Iteration | gh | bar: Feb 1 5 to Feb 8 6
Prepare concept choice workshop | ef | bar: Jan 18 3 to Feb 8 6
Presentation and choice | ef | bar: Feb 15 7
Chosen concept
< press on the '-' to open and close subtasks
< these subtasks can be grouped via data / group /ungroup

## action list
Project name
number | action | subject | who | when | done | result / decision
1 | agree on goal and deliverables | plan | ab |  | y | project plan version confirmed
2 | distribute first version of specifications | specs | cd |  | n
3 | review budget and planning and provide feedback | plan | all |  | y | added 20k unforeseen, added 20k small tooling
4 | update project plan | plan | ab |  | n
5 | place order for concept sketches | concept | ef |  | n
6 |  |  |  |  | n
7 |  |  |  |  | n
8 |  |  |  |  | n
9 |  |  |  |  | n
10 |  |  |  |  | n
11 |  |  |  |  | n
12 |  |  |  |  | n
13 |  |  |  |  | n
14 |  |  |  |  | n
15 |  |  |  |  | n
16 |  |  |  |  | n
18 |  |  |  |  | n
19 |  |  |  |  | n
20 |  |  |  |  | n
21 |  |  |  |  | n
22 |  |  |  |  | n
23 |  |  |  |  | n
24 |  |  |  |  | n
25 |  |  |  |  | n
26 |  |  |  |  | n